## OPD - Summary (hidden)
OPD BUILDING - 483 Workmen
ACTIVITY | PLAN / ACTUAL START | TARGET DATE | PERCENT COMPLETE ON 24.9.26 | PERCENT COMPLETE ON 29.9.26 | REMARKS
[6 empty] | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure |  |  | 100% | 100% | Completed
Finishes
Brickwork | 2025-09-10 | 2026-10-10 | 95% | 97%
Internal Plaster | 2025-11-30 | 2026-10-25 | 95% | 96%
Joineries | 2026-01-25 | 2026-11-15 | 55% | 59% | 70% material is available at site.
Fire door frame & shutter | 2026-03-21 | 2026-10-30 | 45%
Flooring & Dado | 2025-12-18 | 2026-11-25 | 75% | 78% | Material Available
False Ceiling | 2026-07-08 | 2026-12-10 | 5% | 8% | 60% material is available at site.
a) Ground Floor | 2026-07-08 | 2026-10-15 | 20%
b) First Floor | 2026-08-02 | 2026-10-28 | 0%
c) Second Floor | 2026-08-27 | 2026-11-20 | 0%
d) Third Floor | 2026-09-21 | 2026-12-15 | 0%
Lift facia granite | 2026-09-30 | 2026-11-25 | 0% | 4% | Material Available
Interior Works | 2026-10-25 | 2026-12-24 | 0% |  | Material delivery from 20th Oct.
SS Handrail | 2026-11-15 | 2026-12-24 | 0% |  | Material Delivery from 5th Nov
External
Elevation A | 2026-04-04 | 2026-11-15 | 50% | 54% | Façade & Stone available at site
Elevation B | 2026-06-18 | 2026-11-25 | 48% | 53% | Façade & Stone available at site
Elevation C | 2026-08-10 | 2026-12-05 | 30% | 33% | Material Delivery by 15th Oct
Elevation D | 2026-08-25 | 2026-12-15 | 20% | 25% | Material Delivery by 25th Oct
Elevation A | #REF! | 2026-10-20 | 0%
Elevation B | #REF! | 2026-11-05 | 0%
Elevation C | #REF! | 2026-11-22 | 0%
Elevation D | #REF! | 2026-12-05 | 0%
Mechanical Electrical Plumbing ( MEP)
First Fixtures
Cable Tray Installation | 2026-03-12 | 2026-10-20 | 80% | 83%
CI/Gi Piping | 2026-01-28 | 2026-10-31 | 85% | 88%
Ducting & Insulation | 2025-12-11 | 2026-10-27 | 87% | 89%
Fire Piping installation | 2026-01-10 | 2026-10-25 | 86% | 91%
MGPS Copper Piping | 2026-09-10 | 2026-11-25 | 21% | 23% | Material Available
PTTS Pipe installation | 2026-09-10 | 2026-11-15 | 16% | 18% | Material Available
Under deck Insulation | 2026-09-30 | 2026-10-28 | 0% |  | Material Available
Second Fix
Wiring | 2026-08-18 | 2026-11-20 | 38% | 45%
Cable Laying & Panel Instt. | 2026-07-10 | 2026-11-28 | 45% | 51%
UPS Installation | 2026-10-05 | 2026-10-31 | 0% |  | Material delivery by 5th Oct
Dropper Installation | 2026-10-18 | 2026-12-10 | 0% |  | Material delivery by 10th Oct.
HVAC Pipe Testing | 2026-08-10 | 2026-11-10 | 80% | 84%
AHU Connection | 2026-08-19 | 2026-11-28 | 42% | 48%
Wet Riser & FHC installation | 2026-08-10 | 2026-10-24 | 75%
CAT 6 cabling | 2026-08-10 | 2026-11-15 | 38% | 44%
PA & FAS cabling | 2026-07-18 | 2026-11-15 | 52% | 57%
Fire Panel Installation | 2026-09-29 | 2026-10-15 | 0% |  | Material Available
Network Switch | 2026-09-29 | 2026-11-20 | 0% |  | Material Available
Final Fixture | 2026-11-20 | 2026-12-20 | 0% |  | e.g., Light switch, sanitary, WC, etc.
Terrace
PHE Piping installation | 2026-10-10 | 2026-11-15 | 0% |  | Material Available
Solar Panel Installation | 2026-11-05 | 2026-12-10 | 0% |  | Material Delivery by 15th Oct
Over Head Tank | 2026-08-22 | 2026-11-25 | 35% | 44% | Work in progress
Terrace Waterproofing | 2026-08-05 | 2026-12-05 | 75% | 78%
Truss with Polycarbonate Sheet | 2026-09-30 | 2026-10-31 | 60% | 60% | Truss erected Polycarbonate Material Available
Lift Installation with slow speed
2 No.s | 2026-06-05 | 2026-07-30 | 100% | 100%
3 No.s | 2026-08-08 | 2026-10-25 | 65% | 72%
1 No. | 2026-10-11 | 2026-11-28 | 0% |  | Material Available
1 No. | 2026-11-15 | 2026-12-10 | 0% |  | Material Available
Permanent Power
ESS1 to OPD Cable Laying | 2026-09-29 | 2026-10-20 | 0% |  | Material Available
Main LT Panel Energisation | 2026-10-31 | 2026-11-20 | 0% |  | Material delivery by 30th Oct.
Rising Main | 2026-10-28 | 2026-11-25 | 0% |  | Material delivery by 25th Oct
Testing with Permanent Power / Completion
Lift | 2026-12-01 | 2026-12-24
IT/Data Services | 2026-11-25 | 2026-12-20
Fire Control System | 2026-12-05 | 2026-12-24
HVAC System | 2026-11-20 | 2026-12-20
Formulas:
TARGET DATE = VLOOKUP([ACTIVITY],[2]OPD!$B1:D111,3,FALSE)
PLAN / ACTUAL START = MIN([PLAN / ACTUAL START, row below]:B15)
PLAN / ACTUAL START = [PLAN / ACTUAL START, row above]+25

## OPD
OPD (G+3) | Target Date
Brickwork (Shaft Only) | 2026-10-10 | FLOOR | TARGET DATE
Plastering | 2026-10-26 | GF | 2026-10-15
Doors & Windows | 2026-11-15 | FF | 2026-11-20
Flooring & Cladding | 2026-11-25 | SF | 2026-12-10
False Ceiling | 2026-12-10 | TF | 2026-12-25
Toilets | 2026-12-18
Lift works | 2026-11-30
External Finishes | 2026-12-15
Interior works & SS Handrail | 2026-12-24
Power ON | 2026-12-05
HVAC Works | 2026-12-15

## OPD Backup Sheet
OPD BUILDING
ACTIVITY | PLAN / ACTUAL START | TARGET DATE | UOM | Scope | Achieved till on 9th Oct | % Achieved | Balance | Asking Rate | No. of workmen Needed | No. of workmen available | Remarks
Finishes
Brickwork | 2025-09-10 | 2026-10-10 | cum | 4151 | 4115.45 | 99.14% | 35.2455 | 35.2455 | 35 | 65
Internal Plaster | 2025-11-30 | 2026-10-25 | sqm | 50950 | 50087.5 | 98.31% | 847.8993 | 52.9937 | 5 | 7
Joineries | 2026-01-25 | 2026-11-15 | No. | 717 | 378 | 52.72% | 178.7197 | 4.8303 | 2 | 14
Flooring & Dado | 2025-12-18 | 2026-11-25 | sqm | 29200 | 22255 | 76.22% | 5293.1841 | 112.6209 | 38 | 30
False ceiling - GF | 2026-07-08 | 2026-10-15 | sqm | 4152 | 2283.6 | 55% | 1027.62 | 171.27 | 14 | 9
False ceiling - FF | 2026-09-05 | 2026-10-28 | sqm | 3598 | 408 | 11.34% | 361.7343 | 19.0386 | 2 | 5
False ceiling - SF | 2026-11-05 | 2026-11-20 | sqm | 3598 | 0 | 0% | 0 | 0 | 0
False ceiling - TF | 2026-11-30 | 2026-12-15 | sqm | 3715 | 0 | 0% | 0 | 0 | 0
Lift facia granite | 2026-09-30 | 2026-11-25 | sqm | 240 | 0 | 0% | 0 | 0 | 0 |  | Will start from 12th Oct
Interior Works | 2026-10-25 | 2026-12-24 | sqm | 640 | 0 | 0% | 0 | 0 | 0 |  | Drawings & TDS under review
SS Handrail | 2026-11-15 | 2026-12-24 | Rm | 475 | 0 | 0% | 0 | 0 | 0 |  | Drawings will be submitted by 10th Oct
External
Elevation A
Brickwork | 2026-10-13 | 2026-10-20 | sqm | 865 | 825 | 95.38% | 38.1503 | 5.45 | 5 |  | MS Canopy foundation WIP
Plaster | 2026-10-21 | 2026-10-28 | sqm | 1012 | 896 | 88.54% | 102.7036 | 14.6719 | 1
MS framing | 2026-10-01 | 2026-11-07 | sqm | 345 | 27 | 7.826% | 24.887 | 0.85817 | 0 | 4 | Mockup works in progress
Stone Cladding | 2026-10-04 | 2026-11-10 | sqm | 345 | 0 | 0% | 0 | 0 | 0
Glazing | 2026-10-10 | 2026-11-15 | sqm | 669.48 | 0 | 0% | 0 | 0 | 0 |  | Mockup works in progress
Paint | 2026-11-16 | 2026-11-20 | sqm | 1270 | 0 | 0% | 0 | 0 | 0
Elevation B
Brickwork | 2026-10-02 | 2026-10-23 | sqm | 443.4783 | 408 | 92% | 32.64 | 2.3314 | 2 | 4
Plaster | 2026-10-03 | 2026-10-31 | sqm | 780 | 590 | 75.64% | 143.7179 | 6.5326 | 1
MS framing | 2026-10-05 | 2026-11-11 | sqm | 215 | 78 | 36.28% | 49.7023 | 1.5061 | 0 | 11
Stone Cladding | 2026-10-08 | 2026-11-14 | sqm | 215 | 14 | 6.512% | 13.0884 | 0.36357 | 0 | 4
Glazing | 2026-10-16 | 2026-11-21 | sqm | 275.52 | 0 | 0% | 0 | 0 | 0
Paint | 2026-11-22 | 2026-11-25 | sqm | 435 | 0 | 0% | 0 | 0 | 0
Elevation C
Brickwork | 2026-10-04 | 2026-10-30 | sqm | 521 | 497 | 95.39% | 22.8944 | 1.0902 | 1 | 4
Plaster | 2026-10-08 | 2026-11-07 | sqm | 825 | 396 | 48% | 205.92 | 7.1007 | 1 | 5
MS framing | 2026-10-25 | 2026-11-22 | sqm | 285 | 0 | 0% | 0 | 0 | 0
Stone Cladding | 2026-10-28 | 2026-11-25 | sqm | 285 | 0 | 0% | 0 | 0 | 0
Glazing | 2026-10-16 | 2026-12-01 | sqm | 312 | 0 | 0% | 0 | 0 | 0
Paint | 2026-12-02 | 2026-12-05 | sqm | 456 | 0 | 0% | 0 | 0 | 0
Elevation D
Brickwork | 2026-10-15 | 2026-11-05 | sqm | 443.4783 | 425.7391 | 96% | 17.0296 | 0.81093 | 1 |  | Backfilling Works in progress
Plaster | 2026-11-06 | 2026-11-15 | sqm | 780 | 0 | 0% | 0 | 0 | 0
MS framing | 2026-11-05 | 2026-11-22 | sqm | 215 | 0 | 0% | 0 | 0 | 0
Stone Cladding | 2026-11-08 | 2026-11-29 | sqm | 215 | 0 | 0% | 0 | 0 | 0
Glazing | 2026-11-16 | 2026-12-09 | sqm | 275.52 | 0 | 0% | 0 | 0 | 0
Paint | 2026-12-10 | 2026-12-15 | sqm | 435 | 0 | 0% | 0 | 0 | 0
Mechanical Electrical Plumbing ( MEP)
First Fixtures
Cable Tray Installation | 2026-03-12 | 2026-10-20 | Rm | 1500 | 1451 | 96.73% | 47.3993 | 4.309 | 1 | 2
CI/Gi Piping | 2026-01-28 | 2026-10-31 | Rm | 13030 | 10956 | 84.08% | 1743.879 | 79.2672 | 7 | 4
Ducting & Insulation | 2025-12-11 | 2026-10-27 | sqm | 7203 | 6880 | 95.52% | 308.5159 | 17.1398 | 2 | 4
Fire Piping installation | 2026-01-10 | 2026-10-25 | sqm | 9363 | 8880 | 94.84% | 458.0839 | 28.6302 | 2 | 6
MGPS Copper Piping | 2026-09-10 | 2026-11-25 | Rm | 5158 | 421 | 8.162% | 386.6377 | 8.2263 | 1 | 0
PTTS Pipe installation | 2026-09-10 | 2026-11-15 | Rm | 630 | 466.2 | 74% | 121.212 | 3.276 | 0 | 2
Under deck Insulation | 2026-09-30 | 2026-10-28 | sqm | 3426 | 685.2 | 20% | 548.16 | 28.8505 | 3 | 6
Second Fix
Wiring | 2026-08-18 | 2026-11-20 | Rm | 46027 | 23692.96 | 51.48% | 11496.7197 | 273.7314 | 11 | 16
Cable Laying & Panel Instt. | 2026-07-10 | 2026-11-28 | Rm | 16308 | 8643.24 | 53% | 4062.3228 | 81.2465 | 3 | 4
UPS Installation | 2026-10-05 | 2026-10-31 | No. | 4 | 3.6 | 90% | 0.36 | 0.016364 | 0 | 0
Dropper Installation | 2026-10-18 | 2026-12-10 | No. | 1517 | 174 | 11.47% | 154.0422 | 2.9065 | 0 | 0
HVAC Pipe Testing | 2026-08-10 | 2026-11-10 | Rm | 2800 | 2735 | 97.68% | 63.4911 | 1.9841 | 0 | 0
AHU Connection | 2026-08-19 | 2026-11-28 | No. | 45 | 43 | 95.56% | 1.9111 | 0.038222 | 0 | 4
CAT 6 cabling | 2026-08-10 | 2026-11-15 | Rm | 65000 | 20795 | 31.99% | 14142.1996 | 382.2216 | 6 | 8
PA & FAS cabling | 2026-07-18 | 2026-11-15 | Rm | 24107 | 18928 | 78.52% | 4066.3754 | 109.902 | 2 | 4
Fire Panel Installation | 2026-09-29 | 2026-10-15 | No. | 1 | 0 | 0% | 0 | 0 | 0 | 0
Network Switch | 2026-09-29 | 2026-11-20 | No. | 12 | 6 | 50% | 3 | 0.071429 | 0 | 4
Final Fixture | 2026-11-20 | 2026-12-20 | lot | 1 | 0.05 | 5% | 0.0475 | 0.0015833 | 0 | 0
Terrace
PHE Piping installation | 2026-10-10 | 2026-11-15 | rm | 2250 | 202.5 | 9% | 184.275 | 5.1188 | 1 | 7
Solar Panel Installation | 2026-11-05 | 2026-12-10 | No. | 128 | 0 | 0% | 0 | 0 | 0 | 0
Over Head Tank | 2026-08-22 | 2026-11-25 | No. | 1 | 0.75 | 75% | 0.1875 | 0.0039894 | 0 | 0
Terrace Waterproofing | 2026-08-05 | 2026-12-05 | sqm | 3528 | 3528 | 100% | 0 | 0 | 0 | 2
Truss with Polycarbonate Sheet | 2026-09-30 | 2026-10-31 | sqm | 1015 | 659.75 | 65% | 230.9125 | 10.496 | 1 | 2
Lift Installation with slow speed
2 No.s | 2026-06-05 | 2026-07-30 | No. | 2 | 2 | 100% | 0 | 0% | 0 | 0
3 No.s | 2026-08-08 | 2026-10-25 | No. | 3 | 3 | 100% | 0 | 0% | 0 | 0
1 No. | 2026-10-11 | 2026-11-28 | No. | 1 | 0.55 | 55% | 0.2475 | 0.5156% | 0 | 4
1 No. | 2026-11-15 | 2026-12-10 | No. | 1 | 0 | 0% | 0 | 0% | 0 | 2
Permanent Power
ESS1 to OPD Cable Laying | 2026-09-29 | 2026-10-20
Main LT Panel Energisation | 2026-10-31 | 2026-11-20
Rising Main | 2026-10-28 | 2026-11-25
Testing with Permanent Power / Completion
Lift | 2026-12-01 | 2026-12-24
IT/Data Services | 2026-11-25 | 2026-12-20
Fire Control System | 2026-12-05 | 2026-12-24
HVAC System | 2026-11-20 | 2026-12-20
0
Formulas:
Asking Rate = [Balance]/([TARGET DATE]-(IF([PLAN / ACTUAL START]>TODAY(),[PLAN / ACTUAL START],TODAY())))
Asking Rate = [Balance]/([TARGET DATE]-TODAY())
PLAN / ACTUAL START = [TARGET DATE, row above]+1
PLAN / ACTUAL START = [PLAN / ACTUAL START, row above]+3
TARGET DATE = [TARGET DATE, row above]+8
TARGET DATE = [PLAN / ACTUAL START]+4

## EMR
EMR (G+3) | Target Date
Brickwork | 2026-10-25
Plastering | 2026-11-20 | FLOOR | TARGET DATE
Doors & Windows | 2026-11-20 | GF | 2026-10-28
Flooring & Cladding | 2026-11-30 | FF | 2026-11-25
False Ceiling | 2026-12-18 | SF | 2026-12-18
Toilets | 2026-12-28 | TF | 2026-12-25
Lift Works | 2026-12-26
External Finishes | 2026-12-11
Interior works & SS Handrail | 2026-12-24
CSSD | 2026-11-15
Power ON | 2026-12-12
HVAC Works | 2026-12-21
OT Works / ICU | 2026-12-24

## EMR Backup Sheet
EMERGENCY BUILDING
ACTIVITY | PLAN / ACTUAL START | Target Date | UOM | SCOPE | Achieved till 9th Oct | % Achieved | Balance | Asking Rate | Manpower Needed | Manpower Available
Finishes
Brickwork | 2025-10-08 | 2026-10-25 | Cum | 4228 | 4101.16 | 97% | 126.84 | 7.9275 | 8 | 8
Internal Plaster | 2026-01-10 | 2026-11-10 | sqm | 55280 | 44989 | 81.38% | 10291 | 321.5938 | 27 | 30
Joineries | 2026-03-21 | 2026-12-15 | No. | 782 | 445.74 | 57% | 336.26 | 5.0188 | 2 | 0
Flooring & Dado | 2026-02-20 | 2026-11-30 | sqm | 26142 | 21499.02 | 82.24% | 4642.98 | 89.2881 | 9 | 12
False ceiling - GF | 2026-10-15 | 2026-11-20 | sqm | 6228 | 186.84 | 3% | 6041.16 | 167.81 | 14
False ceiling - FF | 2026-10-25 | 2026-11-10 | sqm | 5397 | 0 | 0% | 5397 | 337.3125 | 28
False ceiling - SF | 2026-11-04 | 2026-11-25 | sqm | 5397 | 0 | 0% | 5397 | 257 | 21
False ceiling - TF | 2026-11-14 | 2026-12-10 | sqm | 5572.5 | 0 | 0% | 5572.5 | 214.3269 | 18
Lift lobby | 2026-10-20 | 2026-12-20 | sqm | 290 | 0 | 0% | 290 | 4.7541 | 1 | 0
Interior Works | 2026-11-18 | 2026-12-18 | sqm | 530 | 0 | 0% | 530 | 17.6667 | 2 | 0
SS Handrail | 2026-11-10 | 2026-12-20 | Rm | 475 | 0 | 0% | 475 | 11.875 | 1 | 0
OT Rooms
Ground Floor ( 2 Nos.)
Civil Work | 2026-05-25 | 2026-08-28 |  |  |  | 100% | 100%
OT Works | 2026-08-28 | 2026-10-15 |  |  |  | 54% | 46% |  | 4 | 0
2nd Floor (2 Nos.)
Civil Work | 2026-06-20 | 2026-10-03 |  |  |  | 100% | 0% |  | 8 | 8
OT Works | 2026-10-03 | 2026-10-30 |  |  |  | 12% | 88%
3rd Floor (12 Nos.)
Civil Work | 2026-07-05 | 2026-10-30 |  |  |  | 45% | 55% |  | 10 | 12
OT Works | 2026-10-30 | 2026-12-21 |  |  |  | 0% | 100%
CSSD Room
Civil Work | 2026-07-10 | 2026-08-30 |  |  |  | 100% | 0% | - | -
Service Oriented Work | 2026-09-01 | 2026-11-25 |  |  |  | 58% | 42%
Above Terrace
Staircase - Head Room | 2026-09-15 | 2026-10-30 | CUM | 340 | 129.2 | 38% | 210.8 | 10.0381 | 3 | 3
Over Head Tank | 2026-09-25 | 2026-11-01 | sqm | 350 | 147 | 42% | 203 | 8.8261 | 3 | 4
Terrace Waterproofing | 2026-09-07 | 2026-10-30 | sqm | 3754 | 2552.72 | 68% | 1201.28 | 57.2038 | 6 | 3
Truss & Polycarbonate Sheet | 2026-10-05 | 2026-10-25 | sqm | 884.5 | 610.305 | 69% | 274.195 | 17.1372 | 2 | 0
External
Elevation A | 2026-08-05 | 2026-12-10 | sqm | 935 | 392.7 | 42% | 542.3 | 8.7468 | 3 | 8
Elevation B | 2026-08-18 | 2026-12-12 | sqm | 490 | 68.6 | 14% | 421.4 | 6.5844 | 2 | 5
Elevation C | 2026-09-05 | 2026-12-18 | sqm | 564 | 112.8 | 20% | 451.2 | 6.4457 | 2 | 2
Elevation D | 2026-08-10 | 2026-12-10 | sqm | 485 | 82.45 | 17% | 402.55 | 6.4927 | 2 | 0
Fascia Beam | 2026-09-02 | 2026-11-30 | Rm | 437.6 | 126.904 | 29% | 310.696 | 5.9749 | 2 | 3
Mechanical Electrical Plumbing ( MEP)
First Fixtures
Cable Tray Installation | 2026-01-12 | 2026-09-10 | Rm | 1537 | 1537 | 100% | 0 | 0 | 0 | 0
CI/GI Piping | 2026-01-27 | 2026-12-10 | Rm | 4560 | 3242.4 | 71.11% | 1317.6 | 21.2516 | 5 | 4
Ducting & Insulation | 2026-01-20 | 2026-10-31 | sqm | 9830 | 9633.4 | 98% | 196.6 | 8.9364 | 2 | 5
Fire Piping installation | 2026-01-10 | 2026-12-02 | Rm | 8425 | 5863.25 | 69.59% | 2561.75 | 47.4398 | 12 | 8
MGPS Copper Piping | 2026-09-10 | 2026-12-18 | Rm | 8263 | 2523.12 | 30.54% | 5739.88 | 81.9983 | 20 | 15
PTTS Pipe installation | 2026-10-10 | 2026-12-05 | Rm | 820 | 32.8 | 4% | 787.2 | 14.0571 | 4 | 3
Under deck Insulation | 2026-11-01 | 2026-12-05 | sqm | 3121 | 0 | 0% | 3121 | 91.7941 | 23 | 16
Second Fix
Wiring | 2026-09-03 | 2026-11-27 | Rm | 58034 | 12767.48 | 22% | 45266.52 | 923.8065 | 27 | 18
Cable Laying & Panel Instt. | 2026-09-05 | 2026-11-21 | Rm | 23078 | 9773.86 | 42.35% | 13304.14 | 309.3986 | 23 | 15
UPS Installation | 2026-12-05 | 2026-12-20 | No. | 4 | 0 | 0% | 4 | 0.26667 | 0 | 0
HVAC Pipe Testing | 2026-07-27 | 2026-12-09 | Rm | 2943 | 1500.93 | 51% | 1442.07 | 23.6405 | 6 | 0
AHU Connection | 2026-07-27 | 2026-12-09 | No. | 48 | 14 | 29.17% | 34 | 0.55738 | 0 | 0
CAT 6 cabling | 2026-06-16 | 2026-12-08 | Rm | 58362 | 28013.76 | 48% | 30348.24 | 505.804 | 22 | 19
PA & FAS cabling | 2026-06-16 | 2026-11-27 | Rm | 25900 | 16317 | 63% | 9583 | 195.5714 | 18 | 17
Fire Panel Installation | 2026-10-10 | 2026-10-26 | No. | 1 | 0 | 0% | 1 | 0.0625 | 0 | 0
Network Switch | 2026-10-15 | 2026-12-11 | No. | 14 | 0 | 0% | 14 | 0.24561 | 0 | 0
Final Fixture | 2026-11-20 | 2026-12-10 | Lot | 1 | 0 | 0% | 1 | 0.05 | 0 | 0
Terrace
PHE Piping installation | 2026-10-15 | 2026-11-25 | Rm | 2250 | 1012.5 | 45% | 1237.5 | 30.1829 | 3 | 5
Cable Tray Installation | 2026-10-15 | 2026-11-21 | Rm | 756 | 756 | 100% | 0 | 0 | 0 | 0
Solar Panel Installation | 2026-11-05 | 2026-12-16 | No. | 128 | 0 | 0% | 128 | 3.122 | 0 | 0
Lift Installation with slow speed
2 Nos. | 2026-09-30 | 2026-11-05 | No. | 2 |  | 7% | 93% | 0.5185% | 4 | 6
1 Nos. | 2026-10-07 | 2026-11-18 | No. | 1 |  | 0% | 100% | 0% | 0
2 Nos. | 2026-10-11 | 2026-11-28 | No. | 2 |  | 0% | 100% | 0% | 0
2 Nos. | 2026-11-15 | 2026-12-21 | No. | 2 |  | 0% | 100% | 0% | 0
2 Nos. | 2026-10-24 | 2026-12-08 | No. | 2 |  | 0% | 100% | 0% | 0
2 Nos. (Dumb waiter) | 2026-10-28 | 2026-12-17 | No. | 2 |  | 0% | 100% | 0% | 0
Permanent Power
ESS1 to EMR Cable laying | 2026-09-10 | 2026-10-08
Main LT Panel Energisation | 2026-10-25 | 2026-11-10
Rising Main | 2026-10-28 | 2026-11-15
Testing with Permanent Power / Completion
Lift | 2026-12-01 | 2026-12-24
IT/Data Services | 2026-11-25 | 2026-12-20
Fire Control System | 2026-12-05 | 2026-12-24
HVAC System | 2026-11-20 | 2026-12-20
#N/A
Formulas:
Asking Rate = [Balance]/([Target Date]-(IF([PLAN / ACTUAL START]>TODAY(),[PLAN / ACTUAL START],TODAY())))
Asking Rate = (1-[Balance])*[SCOPE]/([Target Date]-(IF([PLAN / ACTUAL START]>TODAY(),[PLAN / ACTUAL START],TODAY())))
Target Date = VLOOKUP([ACTIVITY],[1]EMR!$B7:D131,3,FALSE)
Target Date = [PLAN / ACTUAL START]+45
PLAN / ACTUAL START = [PLAN / ACTUAL START, row above]+10

## Academic (hidden)
ACADEMIC BUILDING
|  |  | Period Highlight: |  | 2026-10-01 |  |  | Plan Duration |  |  | % Complete
ACTIVITY | PLAN START | Target Date | PERCENT COMPLETE | Remarks | PERIODS
[5 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure |  |  | 100%
Finishes
Brickwork | 2025-07-05 | 2026-09-30 | 95%
Plaster | 2025-08-12 | 2026-10-10 | 84%
Aluminum Joineries | 2026-03-10 | 2026-12-15 | 55%
Fire door frame & shutter | 2026-02-19 | 2026-12-15 | 45%
Flooring & Dado | 2026-02-10 | 2026-11-30 | 65%
False Ceiling | 2026-06-20 | 2026-11-30 | 20%
a) Ground Floor
b) First Floor
c) Second Floor
d) Third Floor
SS Handrail
Above Terrace
OHT Waterproofing & Tiling
LMR
Terrace Waterproofing&HRT Tiles
Pedestals
Polycarbonate Sheet
External (Shaft brickwork & Plaster)
Elevation A
Elevation B
Elevation C
Elevation D
External Stone Cladding
Elevation A
Elevation B
Elevation C
Elevation D
Structural Glazing
Elevation A | 1900-01-04 | 2026-10-20 | 0%
Elevation B | 1900-01-04 | 2026-11-05 | 0%
Elevation C | 1900-01-04 | 2026-11-22 | 0%
Elevation D | 1900-01-04 | 2026-12-05 | 0%
MEP
Second Fix
Electrical | 2026-08-18 | 2026-12-10 | 39%
PHE | 2026-07-28 | 2026-12-26 | 42%
HVAC | 2026-06-30 | 2026-12-18 | 58%
Firefighting | 2026-07-14 | 2026-12-20 | 41%
ELV | 2026-08-03 | 2026-12-25 | 35%
Final Fixture
Electrical
PHE
HVAC
Firefighting
ELV
MGPS
PTTS
Terrace
Solar Panel Installation
DDC Panel Installation
Booster Panel Installation
Shaft
PHE Piping
HVAC Ducting
Rising Main Installation
Cable Tray & Raceway installation
Lift Installation

## EMR - Activity wise (hidden)
EMERGENCY BUILDING - 396 Workmen
ACTIVITY | PLAN / ACTUAL START | TARGET DATE | % COMPLETE ON 24.09.26 | % COMPLETE ON 29.09.26 | REMARKS | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure |  |  | 100% | 100%
Finishes
Brickwork | 2025-10-08 | 2026-10-25 | 95% | 96%
Internal Plaster | 2026-01-10 | 2026-11-10 | 75% | 78%
Joineries | 2026-03-21 | 2026-12-15 | 55% | 57%
Fire door frame & shutter | 2026-03-21 | 2026-12-15 | 45%
Flooring & Dado | 2026-02-20 | 2026-11-30 | 75% | 79%
False Ceiling | 2026-10-28 | 2026-12-22 | 0% |  | Material delivery by 25th Oct.
Lift lobby | 2026-10-20 | 2026-12-20 | 0% |  | Material Available
Interior Works | 2026-11-18 | 2026-12-28 | 0% |  | Material delivery from 15th Nov
SS Handrail | 2026-11-10 | 2026-12-20 | 0% |  | Material delivery from 5th Nov.
OT Rooms
Ground Floor ( 2 Nos.)
Civil Work | 2026-05-25 | 2026-08-28 | 100% | 100%
OT Works | 2026-08-28 | 2026-11-18 | 35% | 38% | Material Available
2nd Floor (2 Nos.)
Civil Work | 2026-06-20 | 2026-10-03 | 95% | 96%
OT Works | 2026-10-03 | 2026-12-05 | 0% | 0% | Material Available
3rd Floor (12 Nos.)
Civil Work | 2026-07-05 | 2026-10-30 | 25% | 27%
OT Works | 2026-10-30 | 2026-12-31 | 0% | 0% | Material Available
CSSD Room
Civil Work | 2026-07-10 | 2026-08-30 | 100% | 100%
Service Oriented Work | 2026-09-01 | 2026-11-25 | 52% | 54%
Above Terrace
Staircase - Head Room | 2026-09-15 | 2026-10-30 | 25% | 33%
Over Head Tank | 2026-09-25 | 2026-11-01 | 35% | 42%
Terrace Waterproofing | 2026-09-07 | 2026-11-12 | 65% | 68%
Truss & Polycarbonate Sheet | 2026-09-05 | 2026-10-25 | 60% | 64% | Truss erected. Sheet fixing works in progress
External
Elevation A | 2026-08-05 | 2026-11-29 | 35% | 38%
Elevation B | 2026-08-18 | 2026-12-12 | 10% | 14%
Elevation C | 2026-09-05 | 2026-12-28 | 5% | 8%
Elevation D | 2026-08-10 | 2026-12-30 | 15% | 17%
Fascia Beam | 2026-09-02 | 2026-11-20 | 19% | 24%
Mechanical Electrical Plumbing ( MEP)
First Fixtures
Cable Tray Installation | 2026-01-12 | 2026-09-10 | 100% | 100%
CI/GI Piping | 2026-01-27 | 2026-12-10 | 60% | 64%
Ducting & Insulation | 2026-01-20 | 2026-10-31 | 97% | 98%
Fire Piping installation | 2026-01-10 | 2026-12-02 | 65% | 69%
MGPS Copper Piping | 2026-09-10 | 2026-12-18 | 20% | 24% | Material Available
PTTS Pipe installation | 2026-10-10 | 2026-12-05 | 0% |  | Material Available
Under deck Insulation | 2026-11-01 | 2026-12-05 | 0% |  | Material Available
Second Fix
Wiring | 2026-09-03 | 2026-11-27 | 15% | 18%
Cable Laying & Panel Instt. | 2026-09-05 | 2026-11-21 | 32% | 37%
UPS Installation | 2026-12-05 | 2026-12-20 | 0% |  | Material Available
Cistern & Sensor Fixing | 2026-07-20 | 2026-11-10 | 39% | 42%
HVAC Pipe Testing | 2026-07-27 | 2026-12-09 | 45% | 47%
AHU Connection | 2026-07-27 | 2026-12-09 | 22% | 25%
CAT 6 cabling | 2026-06-16 | 2026-12-08 | 37% | 42%
PA & FAS cabling | 2026-06-16 | 2026-11-27 | 60% | 63%
Fire Panel Installation | 2026-10-10 | 2026-10-26 | 0% |  | Material Available
Network Switch | 2026-10-15 | 2026-12-11 | 0% |  | Material Available
Final Fixture | 2026-11-20 | 2026-12-10 | 0% |  | e.g., switch socket and light fixtures, Fire Alarm & PA devices, etc.
Terrace
PHE Piping installation | 2026-10-15 | 2026-11-25 | 0%
Cable Tray Installation | 2026-10-15 | 2026-11-21 | 0%
Solar Panel Installation | 2026-11-05 | 2026-12-16 | 0%
OHT | 2026-11-05 | 2026-12-10 | 35% | 41%
Terrace Waterproofing | 2026-09-10 | 2026-12-05 | 75% | 77%
Truss with Polycarbonate Sheet | 2026-09-30 | 2026-11-15 | 0%
Lift Installation with slow speed
2 Nos. | 2026-09-30 | 2026-11-05 | 0% |  | Civil Clearance given. Mat Avl.
1 Nos. | 2026-10-07 | 2026-11-18 | 0% |  | Civil Clearance given. Mat Avl.
2 Nos. | 2026-10-11 | 2026-11-28 | 0% |  | Material Available
2 Nos. | 2026-11-15 | 2026-12-21 | 0% |  | Material Available
2 Nos. | 2026-10-24 | 2026-12-08 | 0% |  | Material Available
2 Nos. (Dumb waiter) | 2026-10-28 | 2026-12-17 | 0% |  | Material Available
Permanent Power
ESS1 to EMR Cable laying | 2026-09-10 | 2026-10-08 | 25% | 29%
Main LT Panel Energisation | 2026-10-25 | 2026-11-10 | 0% |  | Material available
Rising Main | 2026-10-28 | 2026-11-15 | 0% |  | Material available
Testing with Permanent Power / Completion
Lift | 2026-12-01 | 2026-12-24
IT/Data Services | 2026-11-25 | 2026-12-20
Fire Control System | 2026-12-05 | 2026-12-24
HVAC System | 2026-11-20 | 2026-12-20

## Academic (2) (hidden)
ACADEMIC BUILDING
[8 empty] | Plan Duration |  |  | % Complete
ACTIVITY | PLAN / ACTUAL START | TARGET DATE | PERCENT COMPLETE | REMARKS
[5 empty] | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure |  |  | 100%
Finishes
Brickwork | 2025-07-05 | 2026-10-10 | 95%
Internal Plaster | 2025-08-12 | 2026-10-20 | 84%
Joineries | 2026-03-10 | 2026-12-15 | 55%
Flooring & Dado | 2026-02-10 | 2026-11-30 | 65%
False Ceiling | 2026-06-20 | 2026-12-18 | 20%
a) Ground Floor
b) First Floor
c) Second Floor
d) Third Floor
Interior Works | 2026-11-18 | 2026-12-28 | 0% | Material delivery from 15th Nov
SS Handrail | 2026-11-10 | 2026-12-20 | 0% | Material delivery from 5th Nov.
External
Elevation A | 2026-08-05 | 2026-11-29 | 45%
Elevation B | 2026-08-18 | 2026-12-12 | 12%
Elevation C | 2026-09-05 | 2026-12-28 | 28%
Elevation D | 2026-08-10 | 2026-12-30 | 41%
Mechanical Electrical Plumbing ( MEP)
First Fixtures
CI/GI Piping | 2026-07-20 | 2026-12-26 | 45%
Fire Piping installation | 2026-06-29 | 2026-12-15 | 52%
Second Fix
Wiring | 2026-08-18 | 2026-12-10 | 22%
Cable Laying & Panel Instt. | 2026-08-29 | 2026-11-10 | 55%
Dropper Installation | 2026-09-10 | 2026-12-14 | 14%
AHU Connection | 2026-06-22 | 2026-11-15 | 82%
Wet Riser & FHC installation | 2026-07-28 | 2026-12-21 | 42%
CAT 6 cabling | 2026-06-30 | 2026-12-18 | 58%
PA & FAS cabling | 2026-07-14 | 2026-12-20 | 41%
Network Switch | 2026-08-03 | 2026-12-22 | 35%
Lift Installation with slow speed
2 Nos. | 2026-07-29 | 2026-09-12 | 100%
2 Nos. | 2026-10-12 | 2026-12-01 | 0% | Material available
2 Nos. | 2026-10-18 | 2026-12-07 | 0% | Material available
Permanent Power
ESS1 to Academic Cable Laying | 2026-09-10 | 2026-10-08 | 28%
Main LT Panel Energisation | 2026-10-25 | 2026-11-10 | 0% | Material available
Rising Main | 2026-10-28 | 2026-11-15 | 0% | Material available
Testing with Permanent Power / Completion
Lift | 2026-12-01 | 2026-12-24
IT/Data Services | 2026-11-25 | 2026-12-20
Fire Control System | 2026-12-05 | 2026-12-24
HVAC System | 2026-11-20 | 2026-12-20
Formulas:
PLAN / ACTUAL START = [TARGET DATE]-45
TARGET DATE = [PLAN / ACTUAL START]+50

## Type 4 (hidden)
TYPE 4 BUILDING
[7 empty] | % Complete |  |  | Plan Duration
ACTIVITY | PLAN / ACTUAL START | TARGET DATE | PERCENT COMPLETE | REMARKS
[5 empty] | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure |  |  | 100%
Finishes
Brickwork | 2026-05-01 | 2026-09-10 | 100%
Internal Plaster | 2026-05-28 | 2026-09-19 | 100%
Joineries | 2026-06-17 | 2026-11-15 | 29%
Flooring & Dado | 2026-08-08 | 2026-11-10 | 55%
False Ceiling | 2026-09-20 | 2026-10-20 | 0%
Lift Lobby Cladding | 2026-10-20 | 2026-11-09 | 0%
SS Handrail | 2026-10-01 | 2026-11-20 | 0%
Putty + Paint | 2026-09-02 | 2026-11-20 | 25%
External
External Plaster | 2026-06-12 | 2026-09-25 | 95%
External Shaft | 2026-07-09 | 2026-10-30 | 55%
Above Terrace
Over Head Tank | 2026-08-28 | 2026-10-06 | 0%
Terrace Waterproofing | 2026-09-18 | 2026-09-30 | 20%
Mechanical Electrical Plumbing ( MEP)
Frist Fix
Electrical | 2026-05-21 | 2026-09-25 | 96%
PHE | 2026-05-07 | 2026-09-30 | 88%
Firefighting | 2026-07-12 | 2026-09-26 | 90%
ELV | 2026-07-21 | 2026-09-30 | 67%
Second Fix
Electrical | 2026-10-01 | 2026-11-17 | 0%
PHE | 2026-08-29 | 2026-09-19 | 100%
HVAC | 2026-10-30 | 2026-11-15 | 0%
Firefighting | 2026-10-01 | 2026-10-15 | 0%
ELV | 2026-10-30 | 2026-11-25 | 0%
Final Fixture
Electrical | 2026-09-12 | 2026-11-25 | 10%
PHE | 2026-11-01 | 2026-11-30 | 0%
HVAC | 2026-11-10 | 2026-11-30 | 0%
Firefighting | 2026-11-01 | 2026-11-10 | 0%
ELV | 2026-11-11 | 2026-11-20 | 0%
Terrace
PHE Piping installation | 2026-10-01 | 2026-10-20 | 0%
Solar Panel Installation | 2026-11-10 | 2026-11-19 | 0%
DDC Panel Installation | 2026-11-20 | 2026-11-30 | 0%
Booster Panel Installation | 2026-11-20 | 2026-11-30 | 0%
Lift Installation with slow speed
1 Nos.
1 Nos.
Testing with Permanent Power / Completion
Lift
IT/Data Services
Fire Control System
HVAC System

## Type 5 (hidden)
TYPE 5 BUILDING
|  |  | Period Highlight: |  | 2026-09-01 |  |  | Plan Duration |  |  | % Complete
ACTIVITY | PLAN START | Target Date | PERCENT COMPLETE | Remarks | PERIODS
[5 empty] | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01
Structure Above terrace | 2026-04-18 | 2026-09-30 | 96% | Parapet & OHT
Finishes
Brickwork | 2026-06-18 | 2026-09-25 | 94%
Internal Plaster | 2026-07-28 | 2026-10-15 | 58%
External Plaster | 2026-08-17 | 2026-10-20 | 42%
Doors |  | 2026-11-19 | 32%
Windows |  | 2026-12-20 | 26%
Flooring & Dado | 2026-10-01 | 2026-11-14 | 0%
False Ceiling | 2026-09-20 | 2026-10-20 | 0%
a) Ground Floor | 2026-07-08 | 2026-10-15 | 20%
b) First Floor | 2026-08-02 | 2026-10-28 | 0%
c) Second Floor | 2026-08-27 | 2026-11-20 | 0%
d) Third Floor | 2026-09-21 | 2026-12-15 | 0%
Lift lobby cladding | 2026-10-05 | 2026-11-20 | 0%
SS Handrail | 2026-10-01 | 2026-12-20 | 0%
Putty + Paint | 2026-09-02 | 2026-12-30 | 25%
Above Terrace
OHT Waterproofing & Tiling | 2026-08-28 | 2026-10-06 | 0%
External (Shaft brickwork & Plaster) | 2026-03-20 | 2026-10-30 | 59.25%
Elevation A | 2026-03-20 | 2026-08-30 | 100%
Elevation B | 2026-06-10 | 2026-10-10 | 92%
Elevation C | 2026-05-25 | 2026-09-30 | 45%
Elevation D | 2026-06-20 | 2026-10-30 | 0%
Elevation A | 2026-10-06 | 2026-10-15 | 0%
Elevation B | 2026-09-20 | 2026-10-10 | 0%
Elevation C | 2026-10-16 | 2026-10-30 | 0%
Elevation D | 2026-11-01 | 2026-11-15 | 0%
Elevation A | 2026-10-11 | 2026-10-20 | 0%
Elevation B | 2026-09-25 | 2026-11-05 | 0%
Elevation C | 2026-10-21 | 2026-11-22 | 0%
Elevation D | 2026-11-06 | 2026-12-05 | 0%
Terrace waterproofing | 2026-10-05 | 2026-11-05 | 0%
MEP
Frist Fix
Electrical | 2026-07-12 | 2026-11-10 | 44%
PHE | 2026-07-04 | 2026-11-10 | 39%
Firefighting | 2026-10-10 | 2026-11-10 | 0%
ELV | 2026-08-29 | 2026-10-20 | 49%
Second Fix
Electrical | 2026-10-15 | 2026-12-15 | 0%
PHE | 2026-08-21 | 2026-10-10 | 24%
Firefighting | 2026-10-01 | 2026-10-20 | 0%
ELV | 2026-11-19 | 2026-12-18 | 0%
Final Fixture
Electrical | 2026-11-30 | 2026-12-30 | 0%
PHE | 2026-11-30 | 2026-12-29 | 0%
Firefighting | 2026-12-10 | 2026-12-25 | 0%
ELV | 2026-12-20 | 2026-12-30 | 0%
Terrace
PHE Piping installation | 2026-11-01 | 2026-11-30 | 0%
Solar Panel Installation | 2026-12-01 | 2026-12-10 | 0%
DDC Panel Installation | 2026-12-10 | 2026-12-20 | 0%
Booster Panel Installation | 2026-12-20 | 2026-12-30 | 0%
Formulas:
Target Date = VLOOKUP([ACTIVITY],[2]OPD!$B1:D111,3,FALSE)
Target Date = MAX([Target Date, row below]:D27)
PLAN START = [PLAN START, row above]+25
PLAN START = MIN([PLAN START, row below]:C27)

## Type 3 (hidden)
TYPE 3BUILDING
|  |  | Period Highlight: |  | 2026-09-01 |  |  | Plan Duration |  |  | % Complete
ACTIVITY | PLAN START | Target Date | PERCENT COMPLETE | Remarks | PERIODS
[5 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure |  |  | 100%
Finishes
Plaster | 2026-06-12 | 2026-09-30 | 35.49%
Doors | 2026-09-15 | 2026-10-15 | 10%
Windows | 2026-10-01 | 2026-10-30 | 0%
Flooring & Dado | 2026-09-14 | 2026-10-25 | 10%
False Ceiling | 2026-09-20 | 2026-10-20 | 0%
a) Ground Floor | 2026-07-08 | 2026-10-15 | 20%
b) First Floor | 2026-08-02 | 2026-10-28 | 0%
c) Second Floor | 2026-08-27 | 2026-11-20 | 0%
d) Third Floor | 2026-09-21 | 2026-12-15 | 0%
SS Handrail | 2026-10-25 | 2026-11-15 | 0%
Putty + Paint | 2026-09-02 | 2026-11-20 | 25%
Above Terrace
OHT Waterproofing & Tiling | 2026-08-28 | 2026-10-06 | 0%
External (Shaft brickwork & Plaster) | 2026-03-20 | 2026-10-30 | 59.25%
Elevation A | 2026-03-20 | 2026-08-30 | 100%
Elevation B | 2026-06-10 | 2026-10-10 | 92%
Elevation C | 2026-05-25 | 2026-09-30 | 45%
Elevation D | 2026-06-20 | 2026-10-30 | 0%
Elevation A | 2026-10-06 | 2026-10-15 | 0%
Elevation B | 2026-09-20 | 2026-10-10 | 0%
Elevation C | 2026-10-16 | 2026-10-30 | 0%
Elevation D | 2026-11-01 | 2026-11-15 | 0%
Elevation A | 2026-10-11 | 2026-10-20 | 0%
Elevation B | 2026-09-25 | 2026-11-05 | 0%
Elevation C | 2026-10-21 | 2026-11-22 | 0%
Elevation D | 2026-11-06 | 2026-12-05 | 0%
MEP
Frist Fix
Electrical | 2026-05-25 | 2026-08-10 | 100%
PHE | 2026-05-12 | 2026-08-02 | 100%
Firefighting | 2026-09-28 | 2026-10-25 | 0%
ELV | 2026-06-14 | 2026-10-10 | 55%
Second Fix
Electrical | 2026-10-10 | 2026-10-25 | 0%
PHE | 2026-10-08 | 2026-10-25 | 0%
HVAC | 2026-10-14 | 2026-10-25 | 0%
Firefighting | 2026-10-10 | 2026-10-25 | 0%
ELV | 12-0ct | 2026-10-25 | 0%
Final Fixture
Electrical | 2026-10-20 | 2026-11-05 | 0%
PHE | 2026-10-10 | 2026-10-28 | 0%
HVAC | 2026-10-19 | 2026-11-04 | 0%
Firefighting | 2026-10-15 | 2026-10-25 | 0%
ELV | 18-oct` | 2026-10-30 | 0%
Terrace
Solar Panel Installation | 2026-10-16 | 2026-10-29 | 0%
DDC Panel Installation | 2026-10-22 | 2026-11-03 | 0%
Booster Panel Installation | 2026-10-18 | 2026-10-25 | 0%
Formulas:
Target Date = VLOOKUP([ACTIVITY],[2]OPD!$B1:D111,3,FALSE)
Target Date = MAX([Target Date, row below]:D24)
PLAN START = [PLAN START, row above]+25
PLAN START = MIN([PLAN START, row below]:C24)

## UG Female (hidden)
UG FEMALE
|  |  | Period Highlight: |  | 2026-09-01 |  |  | Plan Duration |  |  | % Complete
ACTIVITY | PLAN START | Target Date | PERCENT COMPLETE | Remarks | PERIODS
[5 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure |  |  | 100%
Finishes
Brickwork | 2026-06-08 | 2026-10-15 | 98.66%
Plaster | 2026-07-19 | 2026-10-20 | 35.49%
Aluminum Joineries | 2026-09-12 | 2026-10-10 | 0%
Fire door frame & shutter | 2026-10-01 | 2026-10-10 | 46.15%
Flooring & Dado | 2026-08-08 | 2026-10-15 | 75%
False Ceiling | 2026-09-20 | 2026-10-20 | 0%
a) Ground Floor | 2026-07-08 | 2026-10-15 | 20%
b) First Floor | 2026-08-02 | 2026-10-28 | 0%
c) Second Floor | 2026-08-27 | 2026-11-20 | 0%
d) Third Floor | 2026-09-21 | 2026-12-15 | 0%
SS Handrail | 2026-09-20 | 2026-10-25 | 5%
Above Terrace
OHT Waterproofing & Tiling | 2026-08-28 | 2026-10-06 | 0%
External (Shaft brickwork & Plaster) | 2026-03-20 | 2026-10-30 | 59.25%
Elevation A | 2026-03-20 | 2026-08-30 | 100%
Elevation B | 2026-06-10 | 2026-10-10 | 92%
Elevation C | 2026-05-25 | 2026-09-30 | 45%
Elevation D | 2026-06-20 | 2026-10-30 | 0%
Elevation A | 2026-10-06 | 2026-10-15 | 0%
Elevation B | 2026-09-20 | 2026-10-10 | 0%
Elevation C | 2026-10-16 | 2026-10-30 | 0%
Elevation D | 2026-11-01 | 2026-11-15 | 0%
Elevation A | 2026-10-11 | 2026-10-20 | 0%
Elevation B | 2026-09-25 | 2026-11-05 | 0%
Elevation C | 2026-10-21 | 2026-11-22 | 0%
Elevation D | 2026-11-06 | 2026-12-05 | 0%
MEP
Frist Fix
Electrical
Cable Tray Installation
PHE
CI Pipiing
GI Piping
HVAC
Ducting & Insulation
Firefighting
Piping installation
MGPS
Copper Pipning
PTTS
Pipe installation
Second Fix
Electrical
Wiring
Cable Laying & Panel Installation
UPS Installation
DB Dresssing
PHE
Cister& Sensor Fixing
HVAC
Duct testinfg & dropper for diffusere
Pipe Testing
AHU Connection
Firefighting
Sprinkler Flexible connection & testing
Wet Riser & FHC installation
ELV
CAT 6 cabling
PA & FAS cabling
Fire Panel Installation
Network Switch Installation & connection
MGPS
Copper Pipe testing
PTTS
Pipe accessories fixing & testing
Final Fixture
Electrical
Switch Socket & light fixture Installation
Cable termination & panel testing
UPS testing & commissioning
DB testing
PHE
Fixtures Installation
HVAC
Diffuser Installation
AHU Testing
Firefighting
Sprinkler Fixing
ELV
Fire Alarm & PA Device Fixing
Telephone & Data Socket Fixing
Fire Panel testing & device addressing
Network Switch testing
QMS , HMIS , Biometric , etc.
MGPS
Outlet Installation
PTTS
PTTS station installation
Terrace
PHE Piping installation
Cable Tray, Raceway Installation & cable laying
Solar Panel Installation
DDC Panel Installation
Booster Panel Installation
Shaft
PHE Piping
HVAC Ducting
Rising Main Installation
Cable Tray & Raceway installation
Lift Installation
Formulas:
Target Date = VLOOKUP([ACTIVITY],[2]OPD!$B1:D111,3,FALSE)
Target Date = MAX([Target Date, row below]:D24)
PLAN START = [PLAN START, row above]+25
PLAN START = MIN([PLAN START, row below]:C24)

## UGF backup (hidden)
UG Female Building Balance work Updated 10-09-2026
SL no | Activities | UOM | Scope | Completed | Balance | Strike Date | MEP Clearance | Start Date | Target completion date | Remarks
1 | Brick work | CUM | 1196 | 1180 | 16 |  |  | in progress | 15-10-26 | dipendency external scaffolding Plumbing work
3 | Sand Plastering Internal | Sqm | 5234 | 4900 | 334 |  |  | in progress | 20-10-26 | The false ceiling material stored in the common room will need to be removed
4 | Sand Plastering External | Sqm | 6051 | 5800 | 251 |  |  | in progress | 30-10-26 | Repair & MFH area
5 | Gypsum Plaster | Sqm | 11938 | 11638 | 300 |  |  | in progress | 30-09-26 | Repair
6 | Granite sill Jamb DW1 | SQM | 368 | 368 | 0
6A | Granite sill | Nos | 260 | 230 | 30 |  |  | in progress | 15-10-26 | only fire door & shaft
6B | Granite sill window | Nos | 42 | 32 | 10 |  |  | in progress | 2026-10-30
7 | Granite Dado | Sqm | 105 | 0 | 105 |  |  | aftter lift fixing | 2026-11-10 | after lift completion
8 | Granite Flooring | Sqm | 125 | 0 | 125 |  |  | after lift fixing | 2026-11-11 | after lift completion
8B | Granite counter | Sqm | 35 | 4 | 31 |  |  | in progress | 15-09-26 | work in progress
2 | Sub Frame - Door | Nos | 137 | 137 | 0
9 | Door Frame Room | Nos | 137 | 137 | 0
10 | Flooring Tile | Sqm | 4646 | 0 | 4646 |  | font available | 15-09-26 | 25-10-26 | Agency required
10A | Tile grouting | Sqm | ;4646 | 0 | #VALUE! |  |  | 2026-11-01 | 20-11-26 | Agency required
11 | Skerting Tile | RMT | 2448 | 0 | 2448 |  | font available | 15-09-26 | 25-10-26 | Agency required
12 | Dado Toilet & Staircase | Sqm | 1350 | 60 | 1290 |  | font available | 15-09-25 | 30-10-26 | Team Required & IWC fixing pending all toilet, Juan Dark 450*300 & yana dark 300* 450 tile not available in store
13 | Kota stone flooring | Sqm | 110 | 0 | 110 |  | font available | 15-09-26 | 30-09-26 | Kota stone reached
14 | Internal Painting | Sqm | 17172 | 0 | 17172 |  |  | in progress | 15-11-26 | 1st coat putty startrd
15 | External Painting | Sqm | 5457 | 0 | 5457 |  |  | 2026-10-01 | 20-11-26 | Team required
16 | False ceiling | Sqm | 535 | 0 | 535 |  | MEP Clearence require | 20-09-26 | 20-10-26
17 | Alu. Flush Door | Nos | 137 | 0 | 137 |  |  | 2026-09-12 | 2026-10-10 | Material available
18 | WPC Door | Nos | 86 | 0 | 86 |  | front available | 2026-09-12 | 30-09-26 | team required
19 | Bison Door | Nos | 10 | 0 | 10 |  | front available | Aproval pending | 2026-11-10 | materal and team required
20 | Fire Door | Nos | 26 | 12 | 14 |  | Front available | 2026-10-01 | 2026-10-10 | fire rated tennical issue by client
21 | Alu. DW1 | Nos | 121 | 0 | 121 |  | Front available | 15-09-26 | 30-09-26 | material not available
22 | Alu.Windaw frame | Nos | 42 | 14 | 28 |  | Front available | 15-09-26 | 30-09-26 | material not available
17B | Alu. Flush Door DW1 | Nos | 121 | 0 | 121 |  | front available | 15-09-26 | 30-09-26 | material not available
| GRC MS frame | Nos | 104 | 75 | 29 |  | front available 25 no | 13-09-26 | 16-09-26
23 | GR01 jali | Nos | 104 | 0 | 104 |  | front available 99 no | 2026-09-12 | 25-09-26 | MEP Clearence require
24 | Bolcony Handrail | Nos | 121 | 0 | 121 |  | front available 99 no | 25/09/1900 | 25-10-2026 | Material not received
25 | Brick work | RMT | 484 | 0 | 484 |  |  | 26/09/1900 | 26-10-2026
26 | waterproofing | Sqm | 314.6 | 0 | 242 |  |  | 2026-10-01 | 30-10-2026
27 | Tiling | Sqm | 310 | 0 | 280 |  |  | 2026-11-01 | 15-11-2026
28 | Granite top | Sqm | 97 | 0 | 96 |  |  | 2026-11-01 | 15-11-2026
Terrace UG Female Building Balance work
SL no | Activities | UOM | Scope | Completed | Balance | Strike Date | MEP Clearance | Start Date | Target completion date | Remarks
1 | Brick work | CUM | 63 | 63 | 0
2 | Sand Plastering Internal | Sqm | 180 | 180 | 0 | 0
4 | Sand Plastering External | Sqm | 200 | 120 | 80 | 2 |  | 2026-10-22 | 2026-11-10
5 | Padistal for MEP PHE&HVAC | Nos | 6 | 6 | 0 | 0
6 | Padistal for MEP solar | Nos | 52 | 52 | 0 | 0
7 | Waterpoofing | Sqm | 990 | 0 | 990 | 24.75 |  | work in progress | 30-09-2026
8 | Water tank waterprooging | Sqm | 90 | 45 | 45 |  |  | work in progress | 20-09-2026
9 | Water tank Tiling | Sqm | 90 |  |  |  |  | 2026-01-10 | 2026-10-10 | Team Required
10 | Door fixing | Nos | 3 | 1 | 2 | 2 | front available | 2026-02-10 | 2026-08-10
11 | Parapet Plaster | Sqm | 250 | 150 | 100 | 4.1667 | front available | 2026-05-10 | 2026-10-10
12 | Painting | Sqm | 390 | 0 | 390 | 9.75 |  | 15-10-2026 | 15-11-2026
13 | Manhole cover | Nos | 6 | 0 | 6 |  |  | 15-10-2026 | 20-10-2026
14 | SS Handrail | RMT | 16 | 0 | 16 |  |  | 2026-01-11 | 2026-05-11
15 | Ladder | RMT | 4 | 4 | 0 | 0
16 | Parapet granite Top | RMT | 380 | 0 | 380 |  |  | 2026-11-10 | 20-10-2026
17 | Dog house Brick work with cover slab | Nos | 11 | 0 | 0 |  |  | 2026-10-10 | 20-10-2026
18 | MEP Pedistal By Brick work | Nos | 180 | 0 | 0 |  |  | 2026-10-10 | 15-11-2026
19 | Above terrace painting work | Sqm | 170 | 0 | 0 |  |  | 2026-10-10 | 15-11-2026
Staircase 01 UG Female Building Balance work
SL no | Activities | UOM | Scope | Completed | Balance | Strike Date | MEP Clearance | Start Date | Target completion date | Remarks
2 | Sand Plastering Internal | Sqm | 750 | 700 | 50 |  |  |  |  | Skerting repair
3 | Kota stone flooring | Sqm | 90 | 0 | 90 |  |  | 16-09-2026 | 26-10-2026
5 | Kota stone Riser & Trade | Sqm | 113 | 0 | 113 |  |  | 16-09-2026 | 26-10-2026
6 | Handrail | RMT | 45 |  |  |  |  | 2026-10-10 | 20-10-2026 | Material required
6 | Wall Dado | Sqm | 135 | 0 | 135 |  |  | 15-10-2026 | 30-10-2026
7 | Painting | Sqm | 750 |  |  |  |  | 2026-01-11 | 15-11-2026
Staircase 02 UG Female Building Balance work
SL no | Activities | UOM | Scope | Completed | Balance | Strike Date | MEP Clearance | Start Date | Target completion date | Remarks
2 | Sand Plastering Internal | Sqm | 750 | 700 | 50 |  |  |  |  | Skerting repair
3 | Kota stone flooring | Sqm | 90 | 0 | 90 |  |  | 27-09-2026 | 2026-07-10
5 | Kota stone Riser & Trade | Sqm | 113 | 0 | 113 |  |  | 27-09-2026 | 2026-07-10
6 | Handrail | RMT | 45 |  |  |  |  | 21-10-2026 | 30-10-2026 | Materila required
6 | Wall Dado | Sqm | 135 | 0 | 135 |  |  | 2026-01-11 | 15-11-2026
7 | Painting | Sqm | 750 |  |  |  |  | 15-11-2026 | 30-11-2026
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Terrace 63 cum
Note on F41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Terrace 63 cum

## EMR (hidden)
EMERGENCY BUILDING
|  |  | Period Highlight: |  | 2026-10-01 |  |  | Plan Duration |  |  | % Complete
ACTIVITY | PLAN START | Target Date | PERCENT COMPLETE | Remarks | PERIODS
[5 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure
ST-03 | 2026-09-15 | 2026-10-15 | 25%
ST-04 | 2026-09-01 | 2026-10-10 | 5%
Fascia Beam | 2026-09-02 | 2026-11-30 | 19%
Finishes
Brickwork | 2025-10-08 | 2026-10-25 | 95%
Plaster | 2026-01-10 | 2026-11-10 | 75%
Joineries | 2026-03-21 | 2026-12-15 | 55%
Fire door frame & shutter | 2026-03-21 | 2026-12-15 | 45%
Flooring & Dado |  | 2026-11-30 | 75%
False Ceiling | 2026-07-08 | 2026-12-14 | 5%
a) Ground Floor | 2026-07-08 | #N/A | 20%
b) First Floor | 2026-08-02 | #N/A | 0%
c) Second Floor | 2026-08-27 | #N/A | 0%
d) Third Floor | 2026-09-21 | #N/A | 0%
SS Handrail | 2026-11-10 | 2026-12-20 | 0%
OT Rooms
Above Terrace
OHT&Mummty | 2026-09-25 | 2026-10-15 | 35%
OHT Waterproofing & Tiling | 2026-10-20 | 2026-11-01 | 85.71%
LMR | 2026-02-25 | 2026-10-16 | 75%
Terrace Waterproofing&HRT Tiles | 2026-09-07 | 2026-10-25 | 65%
Pedestals | 2026-09-30 | 2026-10-30 | 0%
Polycarbonate Sheet | 2026-10-05 | 2026-10-25 | 0%
External
Shaft brickwork | 2026-08-05 | 2026-10-20 | 35%
Plaster | 2026-06-10 | 2026-11-05 | 92%
External Stone Cladding | 2026-10-15 | 2026-11-19 | 0%
Structural Glazing | 2026-10-28 | 2026-12-10 | 0%
Elevation A | #REF! | 2026-10-20 | 0%
Elevation B | #REF! | 2026-11-05 | 0%
Elevation C | #REF! | 2026-11-22 | 0%
Elevation D | #REF! | 2026-12-05 | 0%
MEP
Frist Fix
Electrical | 2025-10-10 | 2026-10-10 | 86%
PHE | 2025-09-30 | 2026-10-20 | 91%
HVAC | 2025-11-18 | 2026-09-20 | 100%
Firefighting | 2025-10-25 | 2026-12-02 | 75%
MGPS | 2026-09-20 | 2026-10-30 | 5%
PTTS | 2026-10-05 | 2026-12-10 | 0%
Second Fix
Electrical | 2026-06-18 | 2026-12-30 | 33%
PHE | 2026-03-24 | 2026-10-10 | 45%
HVAC | 2026-04-10 | 2026-12-30 | 29%
Firefighting | 2026-06-12 | 2026-10-10 | 25%
ELV | 2026-06-15 | 2026-12-30 | 15%
MGPS | 2026-07-28 | 2026-12-30 | 0%
PTTS | 2026-10-20 | 2026-12-30 | 0%
Final Fixture
Electrical | 2026-11-30 | 2026-12-30 | 0%
PHE | 2026-11-28 | 2026-12-30 | 0%
HVAC | 2026-10-25 | 2026-12-30 | 0%
Firefighting | 2026-12-10 | 2026-12-30 | 0%
ELV | 2026-11-30 | 2026-12-30 | 0%
MGPS | 2026-11-25 | 2026-12-30 | 0%
PTTS | 2026-12-10 | 2026-12-30 | 0%
Terrace
Solar Panel Installation | 2026-11-10 | 2026-12-30 | 0%
DDC Panel Installation | 2026-11-12 | 2026-12-30 | 0%
Booster Panel Installation | 2026-10-28 | 2026-12-30 | 0%
Shaft |  | 2026-12-30
PHE Piping |  | 2026-12-30
HVAC Ducting |  | 2026-12-30
Rising Main Installation |  | 2026-12-30
Cable Tray & Raceway installation |  | 2026-12-30
Lift Installation | 2026-06-10 | 2026-12-30 | 57.14%
Formulas:
Target Date = VLOOKUP([ACTIVITY],[4]EMR!$B7:D131,3,FALSE)
Target Date = [PLAN START]+35
PLAN START = MIN([PLAN START, row below]:C19)
PLAN START = [PLAN START, row above]+25

## UG Male (hidden)
UG MALE
|  |  | Period Highlight: |  | 2026-09-01 |  |  | Plan Duration |  |  | % Complete
ACTIVITY | PLAN START | Target Date | PERCENT COMPLETE | Remarks | PERIODS
[5 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure |  |  | 100%
Finishes
Brickwork | 2026-06-20 | 2026-09-20 | 98.75%
Plaster | 2026-07-19 | 2026-10-20 | 35.49%
Aluminum Joineries | 2026-09-12 | 2026-10-10 | 0%
Fire door frame & shutter | 2026-10-01 | 2026-10-10 | 46.15%
Flooring & Dado | 2026-08-08 | 2026-10-15 | 75%
False Ceiling | 2026-09-20 | 2026-10-20 | 0%
a) Ground Floor | 2026-07-08 | 2026-10-15 | 20%
b) First Floor | 2026-08-02 | 2026-10-28 | 0%
c) Second Floor | 2026-08-27 | 2026-11-20 | 0%
d) Third Floor | 2026-09-21 | 2026-12-15 | 0%
SS Handrail | 2026-09-20 | 2026-10-25 | 5%
Above Terrace
OHT Waterproofing & Tiling | 2026-08-28 | 2026-10-06 | 0%
External (Shaft brickwork & Plaster) | 2026-03-20 | 2026-10-30 | 59.25%
Elevation A | 2026-03-20 | 2026-08-30 | 100%
Elevation B | 2026-06-10 | 2026-10-10 | 92%
Elevation C | 2026-05-25 | 2026-09-30 | 45%
Elevation D | 2026-06-20 | 2026-10-30 | 0%
Elevation A | 2026-10-06 | 2026-10-15 | 0%
Elevation B | 2026-09-20 | 2026-10-10 | 0%
Elevation C | 2026-10-16 | 2026-10-30 | 0%
Elevation D | 2026-11-01 | 2026-11-15 | 0%
Elevation A | 2026-10-11 | 2026-10-20 | 0%
Elevation B | 2026-09-25 | 2026-11-05 | 0%
Elevation C | 2026-10-21 | 2026-11-22 | 0%
Elevation D | 2026-11-06 | 2026-12-05 | 0%
MEP
Frist Fix
Electrical
Cable Tray Installation
PHE
CI Pipiing
GI Piping
HVAC
Ducting & Insulation
Firefighting
Piping installation
MGPS
Copper Pipning
PTTS
Pipe installation
Second Fix
Electrical
Wiring
Cable Laying & Panel Installation
UPS Installation
DB Dresssing
PHE
Cister& Sensor Fixing
HVAC
Duct testinfg & dropper for diffusere
Pipe Testing
AHU Connection
Firefighting
Sprinkler Flexible connection & testing
Wet Riser & FHC installation
ELV
CAT 6 cabling
PA & FAS cabling
Fire Panel Installation
Network Switch Installation & connection
MGPS
Copper Pipe testing
PTTS
Pipe accessories fixing & testing
Final Fixture
Electrical
Switch Socket & light fixture Installation
Cable termination & panel testing
UPS testing & commissioning
DB testing
PHE
Fixtures Installation
HVAC
Diffuser Installation
AHU Testing
Firefighting
Sprinkler Fixing
ELV
Fire Alarm & PA Device Fixing
Telephone & Data Socket Fixing
Fire Panel testing & device addressing
Network Switch testing
QMS , HMIS , Biometric , etc.
MGPS
Outlet Installation
PTTS
PTTS station installation
Terrace
PHE Piping installation
Cable Tray, Raceway Installation & cable laying
Solar Panel Installation
DDC Panel Installation
Booster Panel Installation
Shaft
PHE Piping
HVAC Ducting
Rising Main Installation
Cable Tray & Raceway installation
Lift Installation
Formulas:
Target Date = VLOOKUP([ACTIVITY],[2]OPD!$B1:D111,3,FALSE)
Target Date = MAX([Target Date, row below]:D24)
PLAN START = [PLAN START, row above]+25
PLAN START = MIN([PLAN START, row below]:C24)

## UG MALE backup (hidden)
UG Male Building Balance work Updated 17-09-2026
SL no | Activities | UOM | Scope | Completed | Balance | Strike Date | MEP Clearance | Start Date | Target completion date | Remarks
1 | Brick work | CUM | 1196 | 1181 | 8 |  |  | in progress | 2026-09-20
3 | Sand Plastering Internal | Sqm | 5234 | 4924 | 310 |  |  | in progress | 20-10-26 | Only drinking area plaster
4 | Sand Plastering External | Sqm | 6051 | 5301 | 750 |  |  | in progress | 2026-09-22 | In progress at MFH area and 2 shaft at D elevation
5 | Gypsum Plaster | Sqm | 11938 | 1170 | 10768 |  |  | in progress | 30-09-26 | Repair work at skirting and dor jamb
6 | Granite sill Jamb DW1 | SQM | 368 | 348 | 20 |  |  | in progress | 20-10-26
6A | Granite sill | Nos | 260 | 220 | 40 |  |  | in progress | 15-10-26 | only fire door & shaft
6B | Granite sill window | Nos | 42 | 35 | 7 |  |  | in progress | 20-10-26
7 | Granite Dado | Sqm | 105 | 0 | 105 |  |  |  |  | Front available, Waiting for material
8 | Granite Flooring | Sqm | 125 | 0 | 125 |  |  |  |  | Completed
8B | Granite counter | Sqm | 35 | 4 | 31 |  |  | in progress | 15-09-26 | work in progress
2 | Sub Frame - Door | Nos | 137 | 137 | 0 |  |  |  |  | Completed
9 | Door Frame Room | Nos | 137 | 137 | 0 |  |  |  |  | Completed
10 | Flooring Tile | Sqm | 4646 | 3830 | 816 |  |  | in progress | 2026-10-10
10A | Tile grouting | Sqm | 4646 | 0 | 4646 |  |  | in progress | 2026-10-15
11 | Skirting Tile | RMT | 2448 | 1713 | 735 |  |  | in progress | 2026-10-10
12 | Dado Toilet & Staircase | Sqm | 1350 | 650 | 700 |  |  | in progress | 2026-10-10 | Team Required & IWC fixing pending all toilet, Juan Dark 450*300 & yana dark 300* 450 tile not available in store
13 | Kota stone flooring | Sqm | 110 | 83 | 27 |  |  | in progress | 2026-09-30
14 | Internal Painting | Sqm | 17172 | 0 | 17172 |  |  | in progress | 2026-10-05 | 1st coat putty in progress at 3rd floor
15 | External Painting | Sqm | 5457 | 0 | 5457 |  |  | 2026-10-01 | 20-11-26 | Team required
16 | False ceiling | Sqm | 535 | 0 | 535 |  | MEP Clearence require | 20-09-26 | 20-10-26 | As per site required height is not available
17 | Alu. Flush Door | Nos | 137 | 0 | 137 |  |  | 2026-09-12 | 2026-10-10 | Material available
18 | WPC Door | Nos | 86 | 0 | 86 |  |  | in progress | 30-09-26 | work in progress
19 | Bison Door | Nos | 10 | 0 | 10 |  | front available |  |  | Approval & materal, team required
20 | Fire Door | Nos | 26 | 12 | 14 |  | Front available | 2026-10-01 | 2026-10-10 | fire rated tennical issue by client
21 | Alu. DW1 | Nos | 121 | 0 | 121 |  | Front available | 15-09-26 | 30-09-26 | material not available
22 | Alu.Windaw frame | Nos | 42 | 14 | 28 |  | Front available | 15-09-26 | 30-09-26 | material not available
17B | Alu. Flush Door DW1 | Nos | 121 | 0 | 121 |  | front available | 15-09-26 | 30-09-26 | material not available
| GRC MS frame | Nos | 104 | 88 | 16 |  |  |  | 16-09-26
23 | GR01 jali | Nos | 104 | 78 | 26 |  |  |  | 2026-09-25 | After Completion f External Plaster
24 | Balcony Handrail | Nos | 121 | 0 | 121 |  |  |  |  | Need aproved GFC drawing
25 | Brick work below railing & Outer Plaster | RMT | 484 | 0 | 484 |  |  |  |  | After Fixing of railing
26 | waterproofing balcony | Sqm | 242 | 0 | 242 |  |  |  |  | After Fixing of railing
27 | Balcony Tiling | Sqm | 310 | 0 | 280 |  |  |  |  | After Fixing of railing
28 | Granite top | Sqm | 96 | 0 | 96 |  |  |  |  | After Fixing of railing
Terrace UG Male Building Balance work
SL no | Activities | UOM | Scope | Completed | Balance | Strike Date | MEP Clearance | Start Date | Target completion date | Remarks
1 | Brick work | CUM | 63 | 63 | 0
2 | Sand Plastering Internal | Sqm | 180 | 180 | 0 | 0
4 | Sand Plastering External | Sqm | 200 | 120 | 80 | 2 |  | 2026-10-03 | 2026-10-23
5 | Padistal for MEP PHE&HVAC - Rcc | Nos | 6 | 6 | 0 | 0
6 | Padistal for MEP solar | Nos | 52 | 52 | 0 | 0
7 | Waterpoofing | Sqm | 870 | 870 | 0 | 0
8 | Water tank waterprooging | Sqm | 90 | 90 | 0
9 | Water tank Tiling | Sqm | 90 |  | 90 |  |  | 2026-10-01 | 6oct.
10 | Door fixing | Nos | 3 | 1 | 2 | 2 | front available |  |  | fire rated tennical issue by client
11 | Parapet Plaster | Sqm | 250 | 250 | 0 | 0 | front available | 2026-10-10 | 15oct.
12 | Painting | Sqm | 390 | 0 | 390 | 9.75 |  | 2026-10-20 | 30oct.
13 | Manhole cover - Tank | Nos | 6 | 0 | 6
14 | SS/ MS Handrail - LMR stair | RMT | 16
15 | Ladder | RMT | 4 | 4 | 0 | 0
16 | Parapet granite Top | RMT | 380 | 290 | 90 |  |  | 2026-10-05 | 2026-10-20
17 | Dog house Brick work with cover slab | Nos | 11 |  | 11 |  |  | 2026-09-24 | 2026-10-10
18 | MEP Pedistal - Brick work | Nos | 180 | 140 | 40 |  |  | 2026-09-20 | 2026-09-25
19 | Above terrace painting work | Sqm | 170 |  | 170 |  |  | 2026-10-20 | 30oct.
Staircase 01 UG Male Building Balance work
SL no | Activities | UOM | Scope | Completed | Balance | Strike Date | MEP Clearance | Start Date | Target completion date | Remarks
2 | Sand Plastering Internal | Sqm | 750 | 700 | 50 |  |  | wip | 2026-10-03 | Skirting repair
3 | Kota stone flooring | Sqm | 90 | 90 | 0 |  |  |  |  | Reparing balance
5 | Kota stone Riser & Trade | Sqm | 113 | 113 | 0 |  |  |  |  | Reparing balance
6 | SS/ MS Handrail | RMT | 45
6 | Wall Dado | Sqm | 135 | 70 | 65
7 | Painting | Sqm | 750 |  |  |  |  | 2026-10-20 | 30oct.
Staircase 02 UG Male Building Balance work
SL no | Activities | UOM | Scope | Completed | Balance | Strike Date | MEP Clearance | Start Date | Target completion date | Remarks
2 | Sand Plastering Internal | Sqm | 750 | 700 | 50 |  |  | wip | 2026-09-30 | Skirting repair
3 | Kota stone flooring | Sqm | 90 | 35 | 55 |  |  | wip | 2026-09-30
5 | Kota stone Riser & Trade | Sqm | 113 | 60 | 53 |  |  | wip | 2026-09-30
6 | SS/ MS Handrail | RMT | 45
6 | Wall Dado | Sqm | 135 | 0 | 135 |  |  | 2026-09-23 | 2026-09-30
7 | Painting | Sqm | 750 |  |  |  |  | 2026-10-20 | 2026-10-30

## OPD (hidden)
OPD BUILDING
|  |  | Period Highlight: |  | 2026-10-01 |  |  | Plan Duration |  |  | % Complete
ACTIVITY | PLAN START | Target Date | PERCENT COMPLETE | Remarks | PERIODS
[5 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Structure |  |  | 100%
Finishes
Brickwork | 2025-09-10 | 2026-10-10 | 95%
Plaster | 2025-11-30 | 2026-10-25 | 35.49%
Joineries | 2026-01-25 | 2026-11-15 | 55%
Fire door frame & shutter | 2026-03-21 | 2026-10-30 | 45%
Flooring & Dado |  | 2026-11-20 | 75%
False Ceiling | 2026-07-08 | 2026-12-15 | 5%
a) Ground Floor | 2026-07-08 | 2026-10-15 | 20%
b) First Floor | 2026-08-02 | 2026-10-28 | 0%
c) Second Floor | 2026-08-27 | 2026-11-20 | 0%
d) Third Floor | 2026-09-21 | 2026-12-15 | 0%
Lift facia granite | 2026-08-18 | 2026-11-25 | 0%
SS Handrail | 2026-10-15 | 2026-11-29 | 0%
Courtyard Plaster inc. Ramp | 2026-07-25 | 2026-10-30 | 33%
Ramp Flooring | 2026-09-25 | 2026-11-25 | 0%
Above Terrace
OHT Waterproofing & Tiling | 2026-07-22 | 2026-11-25 | 35%
LMR | 2026-04-16 | 2026-09-30 | 85.71%
Terrace Waterproofing&HRT Tiles | 2026-08-05 | 2026-12-05 | 75%
Pedestals | 2026-02-09 | 2026-10-05 | 65%
Polycarbonate Sheet | 2026-09-30 | 2026-10-20 | 0%
External (Shaft brickwork & Plaster) | 2026-03-20 | 2026-10-30 | 59.25%
Elevation A | 2026-03-20 | 2026-08-30 | 100%
Elevation B | 2026-06-10 | 2026-10-10 | 92%
Elevation C | 2026-05-25 | 2026-09-30 | 45%
Elevation D | 2026-06-20 | 2026-10-30 | 0%
External Stone Cladding | 2026-09-20 | 2026-11-15 | 0%
Elevation A | 2026-10-06 | 2026-10-15 | 0%
Elevation B | 2026-09-20 | 2026-10-10 | 0%
Elevation C | 2026-10-16 | 2026-10-30 | 0%
Elevation D | 2026-11-01 | 2026-11-15 | 0%
Structural Glazing | 2026-09-25 | 2026-12-05 | 0%
Elevation A | 2026-10-11 | 2026-10-20 | 0%
Elevation B | 2026-09-25 | 2026-11-05 | 0%
Elevation C | 2026-10-21 | 2026-11-22 | 0%
Elevation D | 2026-11-06 | 2026-12-05 | 0%
MEP
Frist Fix
Electrical
Cable Tray Installation | 2025-10-10 | 2026-10-10 | 90%
PHE
CI Pipiing | 2025-09-28 | 2026-09-28 | 95%
GI Piping | 2025-09-22 | 2026-10-20 | 30%
HVAC
Ducting & Insulation | 2025-12-11 | 2026-09-20 | 97%
Firefighting
Piping installation | 2026-01-10 | 2026-09-20 | 90%
MGPS
Copper Pipning | 2026-09-10 | 2026-10-30 | 30%
PTTS
Pipe installation | 2026-09-10 | 2026-10-30 | 20%
Second Fix
Electrical
Wiring | 2026-08-18 | 2026-10-30 | 45%
Cable Laying & Panel Installation | 2026-07-10 | 2026-10-30 | 55%
UPS Installation | 2026-09-28 | 2026-10-10 | 0%
DB Dresssing | 2026-09-10 | 2026-11-10 | 20%
PHE
Cister& Sensor Fixing | 2026-08-25 | 2026-10-10 | 55%
HVAC
Duct testinfg & dropper for diffusere | 2026-10-18 | 2026-12-10 | 50%
Pipe Testing | 2026-08-10 | 2026-10-15 | 80%
AHU Connection | 2026-08-19 | 2026-10-16 | 70%
Firefighting
Sprinkler Flexible connection & testing | 2026-09-10 | 2026-11-14 | 50%
Wet Riser & FHC installation | 2026-08-10 | 2026-10-24 | 75%
ELV
CAT 6 cabling | 2026-08-10 | 2026-11-15 | 45%
PA & FAS cabling | 2026-07-18 | 2026-11-15 | 60%
Fire Panel Installation | 2026-09-29 | 2026-09-30 | 0%
Network Switch Installation & connection | 2026-09-29 | 2026-11-20 | 30%
MGPS
Copper Pipe testing | 2026-11-18 | 2026-12-15 | 0%
PTTS
Pipe accessories fixing & testing | 2026-11-20 | 2026-12-30 | 0%
Final Fixture
Electrical
Switch Socket & light fixture Installation | 2026-09-10 | 2026-12-20 | 10%
Cable termination & panel testing | 2026-10-12 | 2026-11-22 | 0%
UPS testing & commissioning | 2026-10-08 | 2026-10-15 | 0%
DB testing | 2026-10-15 | 2026-10-30 | 0%
PHE
Fixtures Installation | 2026-10-29 | 2026-12-20 | 0%
HVAC
Diffuser Installation | 2026-10-19 | 2026-12-15 | 0%
AHU Testing | 2026-10-25 | 2026-12-25 | 0%
Firefighting
Sprinkler Fixing | 2026-09-12 | 2026-11-25 | 20%
ELV
Fire Alarm & PA Device Fixing | 2026-10-17 | 2026-12-25 | 0%
Telephone & Data Socket Fixing |  | 2026-12-25 | 0%
Fire Panel testing & device addressing |  | 2026-12-25 | 0%
Network Switch testing |  | 2026-12-25 | 0%
QMS , HMIS , Biometric , etc. |  | 2026-12-25 | 0%
MGPS
Outlet Installation |  | 2026-12-30 | 0%
PTTS
PTTS station installation |  | 2026-12-30 | 0%
Terrace
PHE Piping installation |  | 2026-10-27 | 0%
Cable Tray, Raceway Installation & cable laying |  | 2026-10-25 | 0%
Solar Panel Installation |  | 2026-10-25 | 0%
DDC Panel Installation |  | 2026-10-25 | 0%
Booster Panel Installation |  | 2026-10-15 | 0%
Shaft
PHE Piping | 2026-07-01 | 2026-10-30 | 60%
HVAC Ducting | 2026-10-20 | 2026-11-30 | 0%
Rising Main Installation |  | 2026-10-25 | 0%
Cable Tray & Raceway installation |  | 2026-10-25 | 30%
Lift Installation |  | 2026-11-30 | 60%
Formulas:
Target Date = VLOOKUP(B8,[2]OPD!$B1:D111,3,FALSE)
Target Date = VLOOKUP([ACTIVITY],[2]OPD!$B1:D111,3,FALSE)
PLAN START = MIN([PLAN START, row below]:C16)
PLAN START = [PLAN START, row above]+25